## Product Backlog
Product Backlog |  | Sprint
Relative Complexity | Task Detail
Set up Skeleton Application
@ | Learn how to setup and access the API functions through the Spotipy Module | 10/17 - 11/1
@ | Write tutorials/sample programs to hone knowledge over specific aspects of the Module. | 10/17 - 11/1
@@ | Write a setup program that generates a User Profile with a listing of average song qualities | 10/17 - 11/1
@ | Write a user class that we can add mutation functions to, to manipulate the User’s preferences based on comparative songs | 10/17 - 11/1
Set up song fetching
@@@ | Write a procedure to generate a new listing of songs that can be compared to the user’s profile to generate a ranking of new songs that the user will like. | 10/17 - 11/1
@ | Write a program that will generate a new text file that will display the User’s new suggested songs | 10/17 - 11/1
Documentation
@@ | Code Documentation | 10/17 - 11/1
@ | UML stuff | 10/17 - 11/1
Make our code portable with SQLite3
@@ | Extract user profile data to a database | 11/2-11/16
@ | Adapt all setup methods to interact with SQLite | 11/2-11/16
@ | Adapt User class methods to interact with SQLite | 11/2-11/16
Extend the profile to be more useful and dynamic
@@ | Further develop the user profile as its own object | 11/2-11/16
@ | Write methods to calculate and preserved standard deviation of numerical features | 11/2-11/16
@@@ | Write methods and structures to hold weighting of features | 11/2-11/16
Unit Testing
@@@ | Begin Writing testing suite | 11/2-11/16
@@@ | Research sane ways to test recommendation | 11/2-11/16
@ | Write testers for all methods | 11/2-11/16
@ | Write testers for all classes | 11/2-11/16
@ | Write testers for mutators | 11/2-11/16
@@ | Write testers for standard deviation methods | 11/2-11/16
Documentation
@@ | Code Documentation | 11/2-11/16
@@ | UML & chart stuff | 11/2-11/16
Flesh out learning methods
@@@@ | Further develop intelligent recommendations | 11/16-semester end
@@@@ | Write methods to adjust weighting as new songs are added to the profile database | 11/16-semester end
@ | Write methods to automatically reject new songs beyond so many standard deviations | 11/16-semester end
@@@@ | Write methods to gauge how new songs mutate the profile, adjust weights accordingly | 11/16-semester end
Rewrite playlist creation to implement selective recommendation
@ | Refine where songs to be recommended come from on Spotify | 11/16-semester end
Finish formal testing
@@ | Finish testing suite | 11/16-semester end
@@ | Figure out how to "reset" an account for continual testing from scratch | 11/16-semester end
@@ | Write in ways to test recommendation | 11/16-semester end
Make our initial setup more portable (preferably a single install script)
@@@ | Write code to automate the whole process, adding songs at regular intervals of time | 11/16-semester end
@@@ | Write code to automate the process of updating the user profile | 11/16-semester end
Final Documentation
@@ | Code Documentation | 11/16-semester end
@@ | UML & chart stuff | 11/16-semester end

## Sprint 1
Sprint Backlog
Complexity | Detail | Complete?
@ | Learn how to setup and access the API functions through the Spotipy Module | Y
@ | Write tutorials/sample programs to hone knowledge over specific aspects of the Module. | Y
@@ | Write a setup program that generates a User Profile with a listing of average song qualities | Y
@ | Write a user class that we can add mutation functions to, to manipulate the User’s preferences based on comparative songs | Y
@@@ | Write a procedure to generate a new listing of songs that can be compared to the user’s profile to generate a ranking of new songs that the user will like. | Y
@ | Write a program that will generate a new text file that will display the User’s new suggested songs | Y
@@ | Documentation | Y
@ | UML stuff